## Slide 1: Facilities Update
Administrative Council Meeting
October 8, 2018

## Slide 2: Measure J Projects
Parking
Final phase
P8, P11 closed
P9 closes 10/8
Road from University closed 10/8-10/15
All lots reopen 10/15
Overflow parking on grass field

## Slide 3: Current Measure J Projects
Huddle and Mount Vernon Commissary (MVC)
  Kitchen moving in December during break
  Huddle is ready for Food Services
  Will have BC food truck on campus serving food
VRC demolition has begun
  Groundbreaking on November 5
  Scheduled for completion at end of November 2019
Wireless infrastructure project
  Evening work and will improve interior Wi-Fi on campus

## Slide 4: Upcoming Measure J Projects
Campus Center tenants moving to LEV this month
  SGA moving week of 10/8
  Veterans moving week of 10/22
  Health moving week of 10/29
Demolition of Campus Center begins in December
  Groundbreaking date TBD
  Scheduled for completion at end of October 2020

## Slide 5: Upcoming Measure J Projects
Science & Engineering Building
  RFQ process right now
    Selecting a Design-Build team now
  Scheduled for completion in December 2021
Gym
  Advertising for a Design-Build team
    Will select that team within the month
  Scheduled for completion in December 2022
Stadium
  December 15, 2018 through August 31, 2019