## Slide 1
Drop for Non-Payment
Phase I, Phase II, and Phase III Implementation Update
Bakersfield College | Dr. Cesar Jimenez
July 27: enrollment freeze
August 17: drop for non-payment
Notes: Speaker notes: - Frame the update as a three-phase implementation. - Emphasize that communications and support started in fall 2025 and continue today. - Highlight the current enrollment count scheduled for drop and the key dates.

## Slide 2
Three-Phase Approach
How the Outstanding Balance Project has unfolded across two academic years
Phase I
Fall 2025
Student outreach
about outstanding balances
Phase II
Spring 2026
Non-registration holds
on 3,000+ students with
a balance over $200
Phase III
Fall 2026
Drop for
non-payment
(Aug. 17, 2026)
Notes: Speaker notes: - Show the progression from outreach to holds to the planned drop. - Mention the communication strategy and that the project has already moved through two phases.

## Slide 3
Phase II: Spring 2026 Holds
Non-registration holds were placed on students with balances over $200
Spring 2026 holds
3,000+ students were placed on non-registration hold.
Self-resolution
About 1,400 students lifted their own holds.
Support tools
Ellucian Experience portal and messaging supported outreach.
What Phase II showed
• Students responded when they were notified early and repeatedly.
• The online portal and messaging helped students understand what they needed to do.
• The number of students at risk has continued to decline as aid and balances are resolved.
Phase II takeaway
The combination of holds, outreach, and support created an earlier intervention point and helped many students resolve balances before the drop process began.
Notes: Speaker notes: - Highlight that students were supported through the portal and messaging. - Mention that many students lifted holds on their own, demonstrating the value of communication and reminders.

## Slide 4
Phase III: Fall 2026 Drop for Non-Payment
Current implementation dates and outreach efforts
Key Dates
July 27
Enrollment freeze
August 13
Student list due to IT
August 17
Drop for non-payment
The number of students currently scheduled to be dropped has moved from 2,400 last week to 1,907 and now 1,812 today.
Notes: Speaker notes: - Share the three critical deadlines. - Note the decrease in students scheduled for drop. - Mention the ongoing multi-channel outreach campaign.

## Slide 5
Student Outreach and Support
How the College is helping students avoid the drop
Communications
Weekly email and text reminders have been sent since July to encourage students to pay, complete FAFSA/CADAA, or seek support.
Phone outreach
Financial Aid student workers are calling students to answer questions and connect them to campus resources.
FAQ webpage
A Drop for Non-Payment FAQ webpage provides dates, resources, and guidance for students and staff.
Support pathways that keep students enrolled
• FAFSA/CADAA completion
• Payment arrangements when available
• Financial Aid help
• Extended hours and Renegade Nights support
• Re-enrollment guidance after balances are resolved
Since July, staff have been calling, emailing, and texting students to encourage payment, FAFSA/CADAA completion, or other resolution before August 17.
Notes: Speaker notes: - Emphasize that the goal is not just to drop students; it is to help students resolve balances and stay enrolled. - Point to multiple support points: communications, calls, FAQ, and extended hours.

## Slide 6
Workgroup and Governance
Cross-functional implementation with Academic Senate appointees
Workgroup Composition
The Drop for Non-Payment workgroup includes cross-functional partners and Academic Senate appointees to ensure broad input and campus-wide coordination.
The group has helped create the FAQ webpage, refine communications, review policy impacts, and coordinate campus support.
Why this structure matters
• Ensures consistent messaging
• Provides a student-centered response
• Helps identify students who should not be dropped
• Creates a process for reviewing exceptions and coding errors
• Improves coordination across departments
The workgroup also continues to evaluate impacts on enrollment, re-enrollment, outstanding balances, and student success.
Notes: Speaker notes: - Note the cross-functional and Academic Senate representation. - Explain that the FAQ and review process help reduce errors and improve clarity.

## Slide 7
What We Are Watching
How we will measure the impact after August 17
Re-enrollment rate
How many dropped students return after resolving their balance.
Seat backfill
Whether open seats are quickly filled by other students.
Census headcount / FTES
The effect on final enrollment and funding metrics.
Outstanding balances
The amount of debt collected or resolved.
Bottom line: the true impact will be known after census, when we can compare re-enrollment, fill rates, FTES, and outstanding balance reductions.
Notes: Speaker notes: - This slide frames the evaluation metrics. - Emphasize that the drop count alone is not the outcome; the real question is what happens after the drop.

## Slide 8
Thank You
Thank you for your partnership in helping students stay informed, resolve balances, and remain on the path to success.
August 17, 2026
Drop for
Non-Payment
Working together to support students before and after the drop process.
Questions?
Notes: Speaker notes: - End with appreciation and a reminder that support continues. - Invite questions and next-step coordination.