## Sheet1
Kern Community College District - Bakersfield College Measure J Bond Program Major Project Budget Status and Summaries
Project | Building Size (In SF) | Approved Budget (After Bidding) | Final Budget / Expenditures | Project Surplus / Budget Increase | Comments / Notes
Veterans Center | 4715 | 7000000 | 6062150 | 937850 | Surplus moved to contingency
Campus Center ABC Building | 67336 | 43575175 | 46575175 | -3000000 | Substantial unforseen conditions including works to preserve the historic Fireside Room, rebuild the entire comprimised roof of the original Dining Commons and perfom a large number of structural improvements due to the degraded concrete columns. $3 Million waa added to the budget from program contingency to addess the unforseen conditions.
Administrative Services Building | 8219 | 8747000 | 7485729 | 1261271 | Project had mimimal issues and is occupied. Transferred $1.1 Million of unused budget to Welcome Center budget.
Welcome Center | 11636 | 7385960 | 9485960 | -2100000 | Alkali soil conditions comprimised the entire concrete floor and required its full replacement. Additional, the internal concrete structural columns required substantial structural repairs. The building's entry columns are also degraded and are requiring structural improvements. Several internal unforseen conditions required new conduit, electrical wire and panels along plumbing piping replacement. The building was in very poor condition. The $2.1 Million of additional budget came from contigency ($1M) and savings from the Administrative ServicesBuilding ($1.1M). The extra work has extended the project schedule by eight months which had cost impacts. Occupancy is sheduled for December 2022.
Memorial Stadium | NA | 18043697 | 15869897 | 2173800 | The Memorial Stadium budget was increased by the college to add additional improvements including the new scoreboard, infrastructure for future sound system and game management improvements and upgrades to the restrroms, concessions and press box spaces. The project returned over $2M to the program contingency.
Science and Engineering | 68300 | 61959909 | 57101027 | 4858882 | The building project is nearly complete and occupied. There are a few substaintal quality of work and schedule issues currently under negotiation with the Design/Build contractor, Bernards that may equire some of the remaining budget to address but not substaintally.
|  |  |  | 4131803 | Current "net" savings contributed back to the BC Measure J Program for project in design or awaiting bidding.
RR 10-18-2022