Guided Pathways Implementation Team
August 28, 2018 | 1pm-3pm | L215

2018-19 Outcomes

Increase the number and percentage of students who:

- Attempt 15 units in the first term

- Attempt 30 units in the first year

- Complete transfer-level math and English in the first year

- Complete 9 core pathway units in the first year

2018-19 Draft Goals:

- Institutionalize the Guided Pathways Implementation Team work and communication

- Develop and publish maps for all programs of study in the Program Pathways Mapper

- Improve systematic coordination with K-12 partners to improve alignment

- Improve placement practices to become compliant with AB 705; establish a co-requisite support model for college-level English and math courses

- Redesign the work of BC Educational Advisors to directly advance the momentum points

Draft Meeting Minutes

| Time | Item | Lead |
| --- | --- | --- |
| 1-1:10pm | Welcome & Introductions Present: Nick Strobel, Jessica Wojtysiak, Jennifer Johnson, Brynn Schock, Amber Hroch, Lesley Bonds, Billie Jo Rice, Corny Rodriguez, Grace Commiso, Craig Hayward Not present: Steven Holmes (at District Consultation Council) | Rodriguez, Wojtysiak, Bonds |
| 1:10-1:30pm | Review of 17-18 Accomplishments - Lesley Bonds reviewed accomplishments document which includes team and individual member accomplishments related to institutional planning. | Bonds |
| 1:30-2:00pm | Review of 2018-19 Work Plan - Lesley Bonds reviewed draft 2018-19 work plan for GPIT - Group consensus to add a sixth goal focused on enrollment management work: packaging of first term courses, one year registration, addressing priority registration barriers - Billie Jo Rice made recommendation to add Math B4a, Math B22 to the math listings to 3d action - Jennifer Johnson suggested Lesley Bonds will work with Jennifer Marden Serratt to send out the invitation to admin leads of the 2 dates they’re responsible for presenting on their pathways data to College Council and to GPIT - Brynn Schock agreed to serve as lead in providing updates on Education pathway | Rodriguez, Wojtysiak, Bonds |
| 2:00-2:15pm | Multiple Measures 4.0 Update - Discussion about cohort size included in initial analysis; small cohort results in large variation from one summer to the next so it is difficult to draw a definitive conclusion | Hayward |
| 2:15-2:45pm | Accreditation: ISER QFE, Data Prelude - Jessica Wojtsyiak led discussion of BC QFE and provided an overview of CCSSE data regarding academic support services - Lesley Bonds described the key elements of the data prelude of the ISER. Discussion around the GPIT’s involvement in reviewing and providing feedback on the Institution-Set Standards in spring 2018. Confirmed OIE will be adding a standard specifically focused on Associate Degrees for Transfer | Wojtysiak & Hayward |
| 2:45pm | Group Photo |  |