## ISIT goals
Committee Goal #1 | Help with the implementation of SARS-ALRT, the at-risk student flag system for all of our courses.
Action Plan | Create a "SARS-ALRT Response Team" task force of instructional faculty and counselors + IT + DSPS + other student services personnel.
Timeline | C6 grant departments pilot SARS-ALRT starting in mid-Fall (at earliest). Response team form in Spring 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | in progress. Implementation of SARS-ALRT is still waiting for decisions to made at the BC vice-president level on the personnel implementation: who is going to do the follow-up on a particular early-alert need. Also, at the colleges VP and district IT level, need to work out particulars of how SARS-ALRT and Banner will communicate with each other, including making sure that the student contact metrics are consistent with each other.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | ISIT minutes and faculty co-chair reports at www2.bakersfieldcollege.edu/nstrobel/isit and this form.
What recommendations does the committee have for the future? | None
Committee Goal #2 | Implement the work plan coming out of the Sloan Conference in April 2013 and make sure we have the personnel support and training to more effectively use technology in a way leading to more student success.
Action Plan | a. Todd Coston is the lead for "Increase support/infrastructure for online classes". ISIT will help develop the plan for supporting our online courses (staff, training, whatever else we need) and the orientation for online students (this is part of a bigger initiative to create an orientation online for several of our areas including the standard matriculation orientation, ISIT will identify the components needed for the orientation). b. Bill Moseley is the lead for "Increase technology use in the classroom". ISIT will provide oversight and be the primary sounding board for his 0.4 load as Faculty Director of Technology, Innovation, and Professional Development to increase student success in online classes and to improve technology use on campus and online. c. Leah Carter is the lead in the section called "Increase the number of students participating in online classes".
Timeline | Throughout this year. See "Faculty Director of Technology, Innovation, and Prof. Dev. charge" document on the ISIT Committee website for Bill Moseley's action plan. There will be a tool for orientations in any type of class in place sometime this fall semester. Cerro Coso is using an online tool for their orientations that we'd like to use for our online mode of orientations (alongside the face-to-face orientations we will continue to offer).
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | In progress.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | An orientation to the mechanics of Moodle for students is posted at https://moodle.kccd.edu/course/view.php?id=624 . The orientation we give ALL students is undergoing massive overhaul by our current director of outreach. Student Affairs people decided that a system like "Adapt" used at Taft College would be a better fit for BC than Cerro Coso's orientation (Comevo). BC will look at incorporating what is in Adapt (which is a learning management system) into the LMS in use at KCCD: Moodle. Other options specific to online orientation are being explored by the Faculty lead of Tech, Innovation, & Prof Development.
What recommendations does the committee have for the future?
Committee Goal #3 | Continue to advocate for granting waitlisted students equal access to their online and face-to-face classes as the enrolled students.
Action Plan | Academic Senate president will continue discussions with Cerro Coso and Porterville. In the meantime use the partial workarounds for Moodle and InsideBC (Course Studio) posted on the ISIT faculty co-chair's site.
Timeline
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Never got resolved.
What recommendations does the committee have for the future? | In academic senate president's court
Committee Goal #4 | Use the new APR Technology Request form and fix what needs fixing in the information-gathering + decision-making processes. Assess technology usage.
Action Plan
Timeline | ISIT form requests given to ISIT starting in October. ISIT prioritizes requests in November and delivers final prioritization and budget figures at December meeting. Campuswide survey of technology usage and needs in March or April 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | ISIT prioritization complete. Technology climate Survey going out two weeks before Spring Break and closes Thursday of week before Spring Break. Survey will be done with Survey Monkey.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Final ISIT prioritization posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/ISIT%20Requests-201314-priority-26nov13_0.xlsx . Individual program technology assessments from annual update form are posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/Tech%20Assessment%20from%20Program%20Review%20Process%202013-14_0.xlsx . Both of these spreadsheets are in the "Resources" section of the ISIT website. These prioritizations are reflected in the mid-year closing the loop document posted in the "Resources" section of the College Council website at https://committees.kccd.edu/sites/committees.kccd.edu/files/Closing%20the%20loop%20Mid%20Year%20Dec%206%202013_1.pdf . <web address to survey monkey survey >
What recommendations does the committee have for the future? | Analysis of technology climate survey will take place at May ISIT meeting.
Committee Goal #5 | Provide input in the development of the new BC website.
Action Plan | See the current version of the new BC website by clicking the BC Centennial logo at the top of any committee's page on the new Committees website. Demo of website at October meeting. New website is scheduled to "go live" in early January. Website is part of a districtwide unified web platform being developed by the district web development team headed by Dave Barnett.
Timeline | October and November
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Site launched March 17, 2014
What recommendations does the committee have for the future? | Continue to seek input on what new website features are needed
Committee Goal #6 | Re-allocate computers to office desktops using criteria for a multi-tiered allocation scheme that takes into account that some "power users" need more powerful hardware than other users.
Action Plan
Timeline | Preliminary work on criteria in November's technology request discussions and finalize criteria in Spring 2014. Continue trickle down of computer lab computers to office desktops throughout year.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete but ongoing
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | New technology request form has been modified to have two requests: one for classroom and one for non-instructional uses
What recommendations does the committee have for the future? | Use new forms!

## big form
Committee Name | Information Services and Instructional Technology
Co-Chairs | Nick Strobel and Todd Coston
Committee Members | Judy Ahl, Primavera Arvizu, Tim Bohan, Leah Carter, Amber Chiang, Greg Cluff, Brent Damron, Manuel Fernandez, Heidi Forsythe, John Hart, Tracy Lovelace, Gabi Martin, Richard McCrow, Matthew Garrett, Erin Miller, Bill Moseley, Isabel Stierle, Kristin Rabe, Kirk Russell, Ron Schott
Committee Charge | 1. Recommend campus-wide technology policy and procedures. 2. Determine and monitor campus software and hardware standards. 3. Allocate technology resources. 4. Review all significant technology projects. 5. Determine and monitor procedures for obtaining technology services. 6. Establish a system of communication between users, district and campus technology resources, and the Academic Senate. 7. Assess how well the implementation of new technology resources support institutional goals and improve student success. (new this year)
College Goal 1: Student Success
Committee Goal #1 | Help with the implementation of SARS-ALRT, the at-risk student flag system for all of our courses. | means first time goal stated
Action Plan | Create a "SARS-ALRT Response Team" task force of instructional faculty and counselors + IT + DSPS + other student services personnel.
Timeline | C6 grant departments pilot SARS-ALRT starting in mid-Fall (at earliest). Response team form in Spring 2014. | means entry from Todd, Leah, Bill needed
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | in progress. Implementation of SARS-ALRT is still waiting for decisions to made at the BC vice-president level on the personnel implementation: who is going to do the follow-up on a particular early-alert need. Also, at the colleges VP and district IT level, need to work out particulars of how SARS-ALRT and Banner will communicate with each other, including making sure that the student contact metrics are consistent with each other.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | ISIT minutes and faculty co-chair reports at www2.bakersfieldcollege.edu/nstrobel/isit and this form. | means second or third time goal stated (so it’s a repeat)
What recommendations does the committee have for the future? | None
Committee Goal #2 | Implement the work plan coming out of the Sloan Conference in April 2013 and make sure we have the personnel support and training to more effectively use technology in a way leading to more student success.
Action Plan | a. Todd Coston is the lead for "Increase support/infrastructure for online classes". ISIT will help develop the plan for supporting our online courses (staff, training, whatever else we need) and the orientation for online students (this is part of a bigger initiative to create an orientation online for several of our areas including the standard matriculation orientation, ISIT will identify the components needed for the orientation). b. Bill Moseley is the lead for "Increase technology use in the classroom". ISIT will provide oversight and be the primary sounding board for his 0.4 load as Faculty Director of Technology, Innovation, and Professional Development to increase student success in online classes and to improve technology use on campus and online. c. Leah Carter is the lead in the section called "Increase the number of students participating in online classes".
Timeline | Throughout this year. See "Faculty Director of Technology, Innovation, and Prof. Dev. charge" document on the ISIT Committee website for Bill Moseley's action plan. There will be a tool for orientations in any type of class in place sometime this fall semester. Cerro Coso is using an online tool for their orientations that we'd like to use for our online mode of orientations (alongside the face-to-face orientations we will continue to offer).
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | In progress.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | An orientation to the mechanics of Moodle for students is posted at https://moodle.kccd.edu/course/view.php?id=624 . The orientation we give ALL students is undergoing massive overhaul by our current director of outreach. Student Affairs people decided that a system like "Adapt" used at Taft College would be a better fit for BC than Cerro Coso's orientation (Comevo). BC will look at incorporating what is in Adapt (which is a learning management system) into the LMS in use at KCCD: Moodle. Other options specific to online orientation are being explored by the Faculty lead of Tech, Innovation, & Prof Development.
What recommendations does the committee have for the future? | 0
Committee Goal #3 | Continue to advocate for granting waitlisted students equal access to their online and face-to-face classes as the enrolled students.
Action Plan | Academic Senate president will continue discussions with Cerro Coso and Porterville. In the meantime use the partial workarounds for Moodle and InsideBC (Course Studio) posted on the ISIT faculty co-chair's site.
Timeline
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Never got resolved.
What recommendations does the committee have for the future? | In academic senate president's court
College Goal 2: Professional Development
Committee Goal | Implement the work plan coming out of the Sloan Conference in April 2013 and make sure we have the personnel support and training to more effectively use technology in a way leading to more student success.
Action Plan | a. Todd Coston is the lead for "Increase support/infrastructure for online classes". ISIT will help develop the plan for supporting our online courses (staff, training, whatever else we need) and the orientation for online students (this is part of a bigger initiative to create an orientation online for several of our areas including the standard matriculation orientation, ISIT will identify the components needed for the orientation). b. Bill Moseley is the lead for "Increase technology use in the classroom". ISIT will provide oversight and be the primary sounding board for his 0.4 load as Faculty Director of Technology, Innovation, and Professional Development to increase student success in online classes and to improve technology use on campus and online. c. Leah Carter is the lead in the section called "Increase the number of students participating in online classes".
Timeline | Throughout this year. See "Faculty Director of Technology, Innovation, and Prof. Dev. charge" document on the ISIT Committee website for Bill Moseley's action plan. There will be a tool for orientations in any type of class in place sometime this fall semester. Cerro Coso is using an online tool for their orientations that we'd like to use for our online mode of orientations (alongside the face-to-face orientations we will continue to offer).
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | In progress.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | An orientation to the mechanics of Moodle for students is posted at https://moodle.kccd.edu/course/view.php?id=624 . The orientation we give ALL students is undergoing massive overhaul by our current director of outreach. Student Affairs people decided that a system like "Adapt" used at Taft College would be a better fit for BC than Cerro Coso's orientation (Comevo). BC will look at incorporating what is in Adapt (which is a learning management system) into the LMS in use at KCCD: Moodle. Other options specific to online orientation are being explored by the Faculty lead of Tech, Innovation, & Prof Development.
What recommendations does the committee have for the future? | 0
College Goal 3: Communication
Committee Goal #4 | Use the new APR Technology Request form and fix what needs fixing in the information-gathering + decision-making processes. Assess technology usage.
Action Plan
Timeline | ISIT form requests given to ISIT starting in October. ISIT prioritizes requests in November and delivers final prioritization and budget figures at December meeting. Campuswide survey of technology usage and needs in March or April 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | ISIT prioritization complete. Technology climate Survey going out two weeks before Spring Break and closes Thursday of week before Spring Break. Survey will be done with Survey Monkey.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Final ISIT prioritization posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/ISIT%20Requests-201314-priority-26nov13_0.xlsx . Individual program technology assessments from annual update form are posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/Tech%20Assessment%20from%20Program%20Review%20Process%202013-14_0.xlsx . Both of these spreadsheets are in the "Resources" section of the ISIT website. These prioritizations are reflected in the mid-year closing the loop document posted in the "Resources" section of the College Council website at https://committees.kccd.edu/sites/committees.kccd.edu/files/Closing%20the%20loop%20Mid%20Year%20Dec%206%202013_1.pdf . <web address to survey monkey survey >
What recommendations does the committee have for the future? | Analysis of technology climate survey will take place at May ISIT meeting.
Committee Goal #5 | Provide input in the development of the new BC website.
Action Plan | See the current version of the new BC website by clicking the BC Centennial logo at the top of any committee's page on the new Committees website. Demo of website at October meeting. New website is scheduled to "go live" in early January. Website is part of a districtwide unified web platform being developed by the district web development team headed by Dave Barnett.
Timeline | October and November
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Site launched March 17, 2014
What recommendations does the committee have for the future? | Continue to seek input on what new website features are needed
Committee Goal | Help with the implementation of SARS-ALRT, the at-risk student flag system for all of our courses.
Action Plan | Create a "SARS-ALRT Response Team" task force of instructional faculty and counselors + IT + DSPS + other student services personnel.
Timeline | C6 grant departments pilot SARS-ALRT starting in mid-Fall (at earliest). Response team form in Spring 2014.
in progress. Implementation of SARS-ALRT is still waiting for decisions to made at the BC vice-president level on the personnel implementation: who is going to do the follow-up on a particular early-alert need. Also, at the colleges VP and district IT level, need to work out particulars of how SARS-ALRT and Banner will communicate with each other, including making sure that the student contact metrics are consistent with each other.
ISIT minutes and faculty co-chair reports at www2.bakersfieldcollege.edu/nstrobel/isit and this form.
None
Committee Goal | Use the new APR Technology Request form and fix what needs fixing in the information-gathering + decision-making processes. Assess technology usage.
Action Plan
Timeline | ISIT form requests given to ISIT starting in October. ISIT prioritizes requests in November and delivers final prioritization and budget figures at December meeting. Campuswide survey of technology usage and needs in March or April 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | ISIT prioritization complete. Technology climate Survey going out two weeks before Spring Break and closes Thursday of week before Spring Break. Survey will be done with Survey Monkey.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Final ISIT prioritization posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/ISIT%20Requests-201314-priority-26nov13_0.xlsx . Individual program technology assessments from annual update form are posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/Tech%20Assessment%20from%20Program%20Review%20Process%202013-14_0.xlsx . Both of these spreadsheets are in the "Resources" section of the ISIT website. These prioritizations are reflected in the mid-year closing the loop document posted in the "Resources" section of the College Council website at https://committees.kccd.edu/sites/committees.kccd.edu/files/Closing%20the%20loop%20Mid%20Year%20Dec%206%202013_1.pdf . <web address to survey monkey survey >
What recommendations does the committee have for the future? | Analysis of technology climate survey will take place at May ISIT meeting.
College Goal 4: Facilities and Infrastructure
Committee Goal | Implement the work plan coming out of the Sloan Conference in April 2013 and make sure we have the personnel support and training to more effectively use technology in a way leading to more student success.
Action Plan | a. Todd Coston is the lead for "Increase support/infrastructure for online classes". ISIT will help develop the plan for supporting our online courses (staff, training, whatever else we need) and the orientation for online students (this is part of a bigger initiative to create an orientation online for several of our areas including the standard matriculation orientation, ISIT will identify the components needed for the orientation). b. Bill Moseley is the lead for "Increase technology use in the classroom". ISIT will provide oversight and be the primary sounding board for his 0.4 load as Faculty Director of Technology, Innovation, and Professional Development to increase student success in online classes and to improve technology use on campus and online. c. Leah Carter is the lead in the section called "Increase the number of students participating in online classes".
Timeline | Throughout this year. See "Faculty Director of Technology, Innovation, and Prof. Dev. charge" document on the ISIT Committee website for Bill Moseley's action plan. There will be a tool for orientations in any type of class in place sometime this fall semester. Cerro Coso is using an online tool for their orientations that we'd like to use for our online mode of orientations (alongside the face-to-face orientations we will continue to offer).
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | In progress.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | An orientation to the mechanics of Moodle for students is posted at https://moodle.kccd.edu/course/view.php?id=624 . The orientation we give ALL students is undergoing massive overhaul by our current director of outreach. Student Affairs people decided that a system like "Adapt" used at Taft College would be a better fit for BC than Cerro Coso's orientation (Comevo). BC will look at incorporating what is in Adapt (which is a learning management system) into the LMS in use at KCCD: Moodle. Other options specific to online orientation are being explored by the Faculty lead of Tech, Innovation, & Prof Development.
What recommendations does the committee have for the future? | 0
Committee Goal | Use the new APR Technology Request form and fix what needs fixing in the information-gathering + decision-making processes. Assess technology usage.
Action Plan
Timeline | ISIT form requests given to ISIT starting in October. ISIT prioritizes requests in November and delivers final prioritization and budget figures at December meeting. Campuswide survey of technology usage and needs in March or April 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | ISIT prioritization complete. Technology climate Survey going out two weeks before Spring Break and closes Thursday of week before Spring Break. Survey will be done with Survey Monkey.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Final ISIT prioritization posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/ISIT%20Requests-201314-priority-26nov13_0.xlsx . Individual program technology assessments from annual update form are posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/Tech%20Assessment%20from%20Program%20Review%20Process%202013-14_0.xlsx . Both of these spreadsheets are in the "Resources" section of the ISIT website. These prioritizations are reflected in the mid-year closing the loop document posted in the "Resources" section of the College Council website at https://committees.kccd.edu/sites/committees.kccd.edu/files/Closing%20the%20loop%20Mid%20Year%20Dec%206%202013_1.pdf . <web address to survey monkey survey >
What recommendations does the committee have for the future? | Analysis of technology climate survey will take place at May ISIT meeting.
College Goal 5: Oversight & Accountability
Committee Goal #6 | Re-allocate computers to office desktops using criteria for a multi-tiered allocation scheme that takes into account that some "power users" need more powerful hardware than other users.
Action Plan
Timeline | Preliminary work on criteria in November's technology request discussions and finalize criteria in Spring 2014. Continue trickle down of computer lab computers to office desktops throughout year.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete but ongoing
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | New technology request form has been modified to have two requests: one for classroom and one for non-instructional uses
What recommendations does the committee have for the future? | Use new forms!
Committee Goal | Help with the implementation of SARS-ALRT, the at-risk student flag system for all of our courses.
Action Plan | Create a "SARS-ALRT Response Team" task force of instructional faculty and counselors + IT + DSPS + other student services personnel.
Timeline | C6 grant departments pilot SARS-ALRT starting in mid-Fall (at earliest). Response team form in Spring 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | in progress. Implementation of SARS-ALRT is still waiting for decisions to made at the BC vice-president level on the personnel implementation: who is going to do the follow-up on a particular early-alert need. Also, at the colleges VP and district IT level, need to work out particulars of how SARS-ALRT and Banner will communicate with each other, including making sure that the student contact metrics are consistent with each other.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | ISIT minutes and faculty co-chair reports at www2.bakersfieldcollege.edu/nstrobel/isit and this form.
What recommendations does the committee have for the future? | None
Committee Goal | Implement the work plan coming out of the Sloan Conference in April 2013 and make sure we have the personnel support and training to more effectively use technology in a way leading to more student success.
Action Plan | a. Todd Coston is the lead for "Increase support/infrastructure for online classes". ISIT will help develop the plan for supporting our online courses (staff, training, whatever else we need) and the orientation for online students (this is part of a bigger initiative to create an orientation online for several of our areas including the standard matriculation orientation, ISIT will identify the components needed for the orientation). b. Bill Moseley is the lead for "Increase technology use in the classroom". ISIT will provide oversight and be the primary sounding board for his 0.4 load as Faculty Director of Technology, Innovation, and Professional Development to increase student success in online classes and to improve technology use on campus and online. c. Leah Carter is the lead in the section called "Increase the number of students participating in online classes".
Timeline | Throughout this year. See "Faculty Director of Technology, Innovation, and Prof. Dev. charge" document on the ISIT Committee website for Bill Moseley's action plan. There will be a tool for orientations in any type of class in place sometime this fall semester. Cerro Coso is using an online tool for their orientations that we'd like to use for our online mode of orientations (alongside the face-to-face orientations we will continue to offer).
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | In progress.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | An orientation to the mechanics of Moodle for students is posted at https://moodle.kccd.edu/course/view.php?id=624 . The orientation we give ALL students is undergoing massive overhaul by our current director of outreach. Student Affairs people decided that a system like "Adapt" used at Taft College would be a better fit for BC than Cerro Coso's orientation (Comevo). BC will look at incorporating what is in Adapt (which is a learning management system) into the LMS in use at KCCD: Moodle. Other options specific to online orientation are being explored by the Faculty lead of Tech, Innovation, & Prof Development.
What recommendations does the committee have for the future? | 0
Committee Goal | Continue to advocate for granting waitlisted students equal access to their online and face-to-face classes as the enrolled students.
Action Plan | Academic Senate president will continue discussions with Cerro Coso and Porterville. In the meantime use the partial workarounds for Moodle and InsideBC (Course Studio) posted on the ISIT faculty co-chair's site.
Timeline
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Never got resolved.
What recommendations does the committee have for the future? | In academic senate president's court
Committee Goal | Use the new APR Technology Request form and fix what needs fixing in the information-gathering + decision-making processes. Assess technology usage.
Action Plan
Timeline | ISIT form requests given to ISIT starting in October. ISIT prioritizes requests in November and delivers final prioritization and budget figures at December meeting. Campuswide survey of technology usage and needs in March or April 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | ISIT prioritization complete. Technology climate Survey going out two weeks before Spring Break and closes Thursday of week before Spring Break. Survey will be done with Survey Monkey.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Final ISIT prioritization posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/ISIT%20Requests-201314-priority-26nov13_0.xlsx . Individual program technology assessments from annual update form are posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/Tech%20Assessment%20from%20Program%20Review%20Process%202013-14_0.xlsx . Both of these spreadsheets are in the "Resources" section of the ISIT website. These prioritizations are reflected in the mid-year closing the loop document posted in the "Resources" section of the College Council website at https://committees.kccd.edu/sites/committees.kccd.edu/files/Closing%20the%20loop%20Mid%20Year%20Dec%206%202013_1.pdf . <web address to survey monkey survey >
What recommendations does the committee have for the future? | Analysis of technology climate survey will take place at May ISIT meeting.
Committee Goal | Provide input in the development of the new BC website.
Action Plan | See the current version of the new BC website by clicking the BC Centennial logo at the top of any committee's page on the new Committees website. Demo of website at October meeting. New website is scheduled to "go live" in early January. Website is part of a districtwide unified web platform being developed by the district web development team headed by Dave Barnett.
Timeline | October and November
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Site launched March 17, 2014
What recommendations does the committee have for the future? | Continue to seek input on what new website features are needed
College Goal 6: Integration
Committee Goal | Help with the implementation of SARS-ALRT, the at-risk student flag system for all of our courses.
Action Plan | Create a "SARS-ALRT Response Team" task force of instructional faculty and counselors + IT + DSPS + other student services personnel.
Timeline | C6 grant departments pilot SARS-ALRT starting in mid-Fall (at earliest). Response team form in Spring 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | in progress. Implementation of SARS-ALRT is still waiting for decisions to made at the BC vice-president level on the personnel implementation: who is going to do the follow-up on a particular early-alert need. Also, at the colleges VP and district IT level, need to work out particulars of how SARS-ALRT and Banner will communicate with each other, including making sure that the student contact metrics are consistent with each other.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | ISIT minutes and faculty co-chair reports at www2.bakersfieldcollege.edu/nstrobel/isit and this form.
What recommendations does the committee have for the future? | None
Committee Goal | Implement the work plan coming out of the Sloan Conference in April 2013 and make sure we have the personnel support and training to more effectively use technology in a way leading to more student success.
Action Plan | a. Todd Coston is the lead for "Increase support/infrastructure for online classes". ISIT will help develop the plan for supporting our online courses (staff, training, whatever else we need) and the orientation for online students (this is part of a bigger initiative to create an orientation online for several of our areas including the standard matriculation orientation, ISIT will identify the components needed for the orientation). b. Bill Moseley is the lead for "Increase technology use in the classroom". ISIT will provide oversight and be the primary sounding board for his 0.4 load as Faculty Director of Technology, Innovation, and Professional Development to increase student success in online classes and to improve technology use on campus and online. c. Leah Carter is the lead in the section called "Increase the number of students participating in online classes".
Timeline | Throughout this year. See "Faculty Director of Technology, Innovation, and Prof. Dev. charge" document on the ISIT Committee website for Bill Moseley's action plan. There will be a tool for orientations in any type of class in place sometime this fall semester. Cerro Coso is using an online tool for their orientations that we'd like to use for our online mode of orientations (alongside the face-to-face orientations we will continue to offer).
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | In progress.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | An orientation to the mechanics of Moodle for students is posted at https://moodle.kccd.edu/course/view.php?id=624 . The orientation we give ALL students is undergoing massive overhaul by our current director of outreach. Student Affairs people decided that a system like "Adapt" used at Taft College would be a better fit for BC than Cerro Coso's orientation (Comevo). BC will look at incorporating what is in Adapt (which is a learning management system) into the LMS in use at KCCD: Moodle. Other options specific to online orientation are being explored by the Faculty lead of Tech, Innovation, & Prof Development.
What recommendations does the committee have for the future? | 0
Committee Goal | Continue to advocate for granting waitlisted students equal access to their online and face-to-face classes as the enrolled students.
Action Plan | Academic Senate president will continue discussions with Cerro Coso and Porterville. In the meantime use the partial workarounds for Moodle and InsideBC (Course Studio) posted on the ISIT faculty co-chair's site.
Timeline
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | Complete
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Never got resolved.
What recommendations does the committee have for the future? | In academic senate president's court
Committee Goal | Use the new APR Technology Request form and fix what needs fixing in the information-gathering + decision-making processes. Assess technology usage.
Action Plan
Timeline | ISIT form requests given to ISIT starting in October. ISIT prioritizes requests in November and delivers final prioritization and budget figures at December meeting. Campuswide survey of technology usage and needs in March or April 2014.
Indicate the status of the goal (complete, in progress, other) and briefly describe the progress made on the goal. | ISIT prioritization complete. Technology climate Survey going out two weeks before Spring Break and closes Thursday of week before Spring Break. Survey will be done with Survey Monkey.
Where is the evidence? List evidence and cite relevant data strands (indicators) that relate to the work that has been done. | Final ISIT prioritization posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/ISIT%20Requests-201314-priority-26nov13_0.xlsx . Individual program technology assessments from annual update form are posted at https://committees.kccd.edu/sites/committees.kccd.edu/files/Tech%20Assessment%20from%20Program%20Review%20Process%202013-14_0.xlsx . Both of these spreadsheets are in the "Resources" section of the ISIT website. These prioritizations are reflected in the mid-year closing the loop document posted in the "Resources" section of the College Council website at https://committees.kccd.edu/sites/committees.kccd.edu/files/Closing%20the%20loop%20Mid%20Year%20Dec%206%202013_1.pdf . <web address to survey monkey survey >
What recommendations does the committee have for the future? | Analysis of technology climate survey will take place at May ISIT meeting.
2013-14 SUMMARY
How are you evaluating your committee's effectiveness in meeting college goals and your committee charge? | Committee discussions at end of year
What did your evaluation reveal?
How will you use your findings to effect positive change? | Helps sets goals for next year so we know what needs improvement