## Sheet1
ISIT Program Review Technology Requests 2015-16
Priority | Description | Complete | Funding Source | Notes
1 | SS 117/206 Short Throw Projector Project | Complete | Title V | Grant allowed us to add 2 70" LED's to SS 117 and 128, allowed for new projectors in SS 122 and 206. SS 122 and 206 will be completed during the Fall semester.
2 | Language Arts Building - Wifi | Partially Complete | GUI | Two new access points have been put on the first floor in rooms # and #. One access point has been added to the second floor in room #.
3 | DST-126 (Delano) 14 Computers Replacement | Partially Complete | GUI | At the site and will be installed during Winter Break.
4 | IT201 Classroom Refresh | Complete | Nursing | Projector was swapped out in IT201 with new - purchased by Nursing
5 | Wifi & 5 Projector/Computer carts | Partially Complete | GUI | When new projectors are added in Delano, the older projectors will be used to make the carts.
6 | LA-113 - Short throw projector | Complete | GUI | LA 113 had a new install of a short throw projector
7 | Ford IDS Diagnostic Equipment | Unfunded |  | Possible purchase by grant.
8 | Chrysler Diagnostic Equipment | Unfunded |  | Possible purchase by grant.
9 | Delano classroom A/V and computer refresh | Partially Complete | GUI | Computers were swapped out for new. Projectors will be complete this Fall
10 | Math Science A/V and computer refresh | Partially Complete | STEM | MS 14 and 17 received swapped out projectors from Biology when they received new from a grant. MS 9 and 10 computers replaced.
11 | Student Services A/V and computer refresh | Complete |  | See the first request - same item
12 | Forum A/V and computer refresh | Unfunded
13 | Language Arts A/V and computer refresh | Unfunded
14 | Science & Engineering Lecture Halls - replacement doc cams | Complete | STEM
15 | FACE A/V and computer refresh | Unfunded
16 | (duplicate of #15) | Choose One:
17 | Business - doc cam cabling | Unfunded
18 | Humanities A/V and computer refresh | Unfunded
19 | INDT printers (5, 6, 7a) | Unfunded | GUI
20 | INDT 7a - 22 replacement computers | Complete | Instructional | Only 15 computers needed for lab.
21 | Communication - laptop cart | Unfunded
22 | FA-65 - upgrade to Short throw projector and replacement computer | Partially Complete |  | FA 65 received a swap out previously used projector for the old projector
23 | Humanities - improve wifi | Unfunded
24 | FA 60- upgrade to short throw project and replace computer | Unfunded
25 | SS 206 or 3a - new computer lab | Unfunded
26 | FA 8 - New computer lab | Complete | Instructional/VTEA | Required for new Digital Arts program.

## Sheet2
Choose One:
Complete
Partially Complete
Unfunded