| DRAFT Accreditation Self Evaluation Calendar |  |  |  |
| --- | --- | --- | --- |
| Timeline | Activity |  | People Responsible |
| 2016 |  |  |  |
| Late September/ October |  | Planning begins; AIQ develops recommendations | AIQ gets started |
| November |  | AIQ Co-Chairs work with President and Accreditation Liaison Officer (ALO) to develop and finalize plan for Self Evaluation | AIQ; President; ALO; Academic Senate; College Council |
| November/ December |  | Attend Academic Senate and College Council meetings to introduce plan | AIQ Co-Chairs |
| December 16 |  | Soft Roll Out | College Council, Co-Chairs, President’s Cabinet, AIQ |
| December |  | Identify Self Evaluation Co-Chairs and Assessment for Accreditation lead | Sonya Christian Nan Gomez-Heitzeberg |
| 2017 |  |  |  |
| January 11 & 12 |  | QFE (part of Winter Institute) | Janet Fulks Mark Staller |
| January 13 |  | Opening Day Roll Out | Sonya, Nan, Kate, Mark |
| January |  | Identify editor |  |
| January 26 |  | Accreditation Training for Co-Chairs and Leads | AIQ |
| January |  | SE and QFE Leads meet, confirm Quality Focus Essay (QFE) topic(s), introduce QFE topic to Academic Senate and College Council | Self Evaluation Co-Chairs; QFE Leads, Standards Leads; AIQ |
| 2017, continues |  |  |  |
| February/March ongoing |  | Research—Answer the questions on your standard, found in this manual: http://www.accjc.org/wp-content/uploads/2016/12/Guide_to_Evaluating_and_Improving_Institutions_Aug-2016_REVISED.pdf Problem Identification and Solving Evidence Collecting Writing | Teams |
| March 31 |  | Accreditation Laboratory (location to be determined): For All Teams (Self Evaluation & Quality Focus Essay) | AIQ |
| April |  | Progress update; identify summer plans | Teams; AIQ |
| Due May 1 Draft 1 |  | A template will be provided. Your response includes: - Evidence of Meeting the Standard (summary with links to evidence) - Analysis and Evaluation Also, plan to identify any gaps in information and evidence that may exist. | Co-Chairs; Leads |
| May/summer |  | Work continues; Self Evaluation Summer Institute (date TBD) | Teams |
| August |  | Reconvene: update on progress and issues | SE & QFE Co-Chairs and teams |
| September 8 |  | Workshop for all teams (SE & QFE) (date TBD) | AIQ; SE & QFE Co-Chairs, Teams |
| October 6 Draft 2 |  |  | Turned in by SE & QFE Co-Chairs and teams; Reviewed by Editor & AIQ |
| October 23 |  | Drafts returned (may be ready to skip Draft 3 and move to Final Draft) |  |
| November 13 Draft 3 as needed |  | Draft 3 (if extra time needed) | Turned in by SE & QFE Co-Chairs and teams; Reviewed by Editor & AIQ |
| December 1 |  | Drafts returned |  |
| December 15 Final Draft |  | Final Draft completed | Teams |
| December 18-21 |  | Draft reviewed for completeness | SE & QFE Co-Chairs & Editor |
| 2018 |  |  |  |
| January 2 |  | Final Draft to Editor | Editor |
| January 31 |  | Editing completed | Editor |
| February/March |  | Layout work occurs while college community reviews document content. | TBD |
| February/March |  | College review and discussion | College Council; Academic Senate; focus groups/forums/online input |
| March |  | Revision as needed based on college review and discussion | Team and Editor |
| April |  | Approval by Academic Senate and College Council | SE & QFE Co-Chairs |
| April |  | Evidence Linking and Printing | Sondra Keckley |
| May |  | Self Evaluation posted in Board Docs for board approval the following month | Jennifer Marden |
| June |  | BOT approval of Self Evaluation | Board of Trustees (BOT) |
| August |  | Self Evaluation due to ACCJC | Jennifer Marden |
| October |  | Site Team Campus Visit |  |

Version 6, January 25, 2017 Kate Pluta