# ISIT Committee

10/2/2023, Via Zoom

# List of Membership

## Co-Chairs:

Faculty Co-Chair: Dr. Bill Moseley

Administrator Co-Chair: Brett Redd

Classified Co-Chair: Kristin Rabe

## In attendance: Members:

Kristin Rabe; Bill Moseley; Brett Redd; Erin Miller; Richard Marquez; James Selgrath; Richard Miles; Kathryn Wright; Kurt Klopstein; Dan Hall; Michael Muhume; Sara Manuel; Kalina Hill; Kirk Russell; Leah Carter; Kimberly Chin; Heather Shaffstall; Scott Peat; Israel Mendoza; Christina Rodriguez; Amanda Brucker; Denice McCauly; Raya Arafah (BCSG); Darren Willis; Priyanka Longacre; Matt Moon; Champagne Concepcion; and Bonnie Hammond

Absent: Tim Bohan; Stephanie Baltazar; William Velasquez

# Called to Order

- Bill Moseley called the meeting via zoom to order at 4:00 pm

# Approval of Agenda

- Approval of Agenda

  - Motioned by Richard Marquez

  - Seconded by Erin Miller

  - Approved Unanimously

# Approval of Meeting Minutes

- Approval of Meeting Minutes

  - Motioned by Darren Willis

  - Seconded by Kristin Rabe

  - Approved Unanimously

# BC-All Policies

- Can be shared with staff/faculty

- Technology Use Policy-Info Only

  - Be aware of using personal devices on network

  - Personal Data not monitored

  - Work related accounts can be monitored

  - A Fairly Use Tale-rules of fair use and copyright

# Technology Plan

- Number of Computers doubled

- Staffing has not changed

- Moved away from video production/live streaming

- Initiatives met/still working on

- New initiatives

- Acadmemic Tech will make needed changes

- No Vote Today

- Strategic Directions will constantly be adjusted as needed

- Student Success Technology also need to be addressed

# Accreditation-Info Only

- Shorter ISER

- Evidence/Evidence Gathering

# Construction updates Brett Redd

- Delano Completed

- Arvin Campus is under construction

- Projects nearing completion & delays:

- Athletic Center

- Had to create a new plan to install communication wires, etc. because the plan to run them under the old pool buildings is no longer viable due to the buildings being condemned

- Rerouting of these wires won’t occur until March 2024, which pushed back the gym floor and other installations that have to be completed in environmentally controlled conditions

- New timeline for the new Athletic Center completion is Spring 2025

- Architects working to determine how to reconstruct old swim buildings

- Ag Building

- Will undergo total tear down and rebuild

- Demo plan for last semester stalled because bids were over budget

- Out for re-bid

- New bids arrived last week

- Tear down now expected Nov 2023

- Ag instructors teaching in general sciences for the next year or two

- Some concern about timing of building new pool houses prior to a new Ag building

- Important to consider the age of our campus creates unexpected delays

- Residence Hall

- Still being discussed-no funding

- High Flex

- Liberal Arts (LA) high flex rooms are nearly complete

- Tech team is working on additional 4 high flex rooms now with 13 more planned for the spring

- This provides an additional 53 high flex rooms by the end of the 2023-2024 academic year in addition to those in the LA building

- Delays for High Flex Rooms:

- LA building faced some delays due to AC problems over the summer

- Humanities building bathroom and windows projects prevented high flex installations over the summer: please be flexible with classrooms if the tech team needs access to your class for a day or two. Schedule zoom classes, labs, or research days, etc. Be prepared for temporary classroom reassignment.

- Training for High Flex

- Academic Tech,  Alex  and Matt are providing training on high flex

- Committee members communicate to deans and chairs in the Humanities and LA about potential temporary classroom reassignments

# Technology Support Services

- Laptop Carts-Complete before end of school year

# Academic Technology Updates

- Ticketing system for Academic Technology

  - Looking into one single ticketing system

  - Pronto-Faculty input and communication

- Zoom Rooms

  - Will be for use with laptops/chomebooks

  - Will be installed by next week

  - 10 Booths

# Upcoming Noteables

- Nov 27th- Special Meeting will be longer-ISIT Request Prioritization Meeting

- ISIT Requests due by Tuesday 10/10/2023

- Next Meeting: Nov 6th- 4:00PM via Zoom

# Meeting Adjourned